## Introduction
Digital Products — Discovery Sessions Workbook
New Ways of Working
Purpose
This workbook is the operational guide for all 7 Initial Discovery Sessions in Weeks 1-2 of the Digital Product project. Each tab contains the key questions to answer, context from the proposal, and space to capture responses and findings. Use this as the single source of truth for all baseline research.
Sessions Overview
Session | Number of Sessions | Duration | Purpose
1. Stakeholder Interviews | 6-10 sessions | 45 min each | Strategic priorities & pain points
2. Demand Sources Mapping | 1-2 sessions | 90-120 min | Map all entry points & channels
3. Portfolio Review | 1-2 sessions | 90-120 min | Full inventory of initiatives
4. Tool Ecosystem Review | 1-2 sessions | 90-120 min | Assess tools & fragmentation
5. Capacity & Resource Model | 1 session | 60-90 min | Team structure & constraints
6. Reporting & Metrics Review | 1 session | 60-90 min | Current KPIs & visibility gaps

## 1. Stakeholder Interviews
1. Stakeholder Interviews
Understand strategic priorities, operational challenges, and current pain points from both leadership and operational perspectives.
| Participants: | Executive Sponsor, CORE Team and Champions, BRS leadership 6-10 individual interviews
| Duration: | 45 minutes each | Reducir a 45´
Para cada stakeholder principal tenemos que entender mejor los blind spots, Carlos (Corporate y GISS), Kumar (lista de apps, sensibilidad de negocio), tener de base para el stakeholder su org chart, la sensibilidad de lo que ya conocemos para cerrar el gap de negocio
No. | Category | Question | Response / Findings | Ana Comments
1 | Role & Context | What is your role and how do you interact with Digital Products? How is your role changing with the new CIO direction and transformation focus? |  | Cómo está cambiando su rol actualmente por el contexto de transformación con el nuevo CIO, nuevas directrices y foco de los próximos años y cómo podemos ayudar y soportar a la persona gracias a llevar a cabo este proyecto
2 | Strategic Priorities | What are your top priorities for the next 6 months?
3 | Delivery Process | Describe how a typical request goes from idea to delivery today.
4 | Pain Points | Where do you experience the most friction or delays?
5 | Prioritization | How do you currently prioritize work? Let's discuss at two levels: (a) how the department prioritizes across areas, and (b) how you personally prioritize within your area. |  | Hablemos en dos niveles como cree que lo hace el dpto y como lo hace su area / él o ella
6 | Tooling | What tools do you use for tracking work? (Jira, ServiceNow, Excel, email?) |  | Combinar siempre el delivery process / stream mapping con el uso de tools y pantallazos / ejemplos
7 | Visibility | How do you get visibility into what's being worked on? |  | Tener de base el governance que hayan descrito / reuniones activas
8 | Pain Points | If you could fix one thing about how Digital Products operates today, what would it be?
9 | Outcome Measurement | What would make you say this project was a success?
10 | Governance | How are decisions escalated when there's a conflict between teams or priorities?
11 | Visibility | What information do you need but currently don't have access to?
12 | Performance | How do you measure the value delivered by Digital Products to your area?
13 | Pain Points | If you could fix one thing about how work gets done today, what would it be? | [REMOVED — Duplicate of Q8 per Ana] | Duplicada con la 8
14 | Alignment | How is alignment ensured between Digital Products, BRS, and other consuming areas? |  | Tener de base el governance que hayan descrito / reuniones activas
15 | Decision Making | Where do you see silos that need to be connected as part of the future operating model? Is decision-making centralized or distributed? |  | donde ves silos que necesitan ser conectados como parte de nuestra definicion to be
16 | Pilot & Adoption | How do you think the pilot could work for your area, and what would it take to scale it across the rest of the department? |  | La cambiaría porque ya conocemos mucho su cultura, no es abierta, transformarla a como crees que el piloto podría funcionar, y para el resto del departamento el journey que empredemos, tips o consideraciones desde su punto de vista
17 | Risks | What do you think is the biggest risk if we don't change how Digital Products operates?
18 | Open Input | Is there anything you think we should know that we haven't asked?
SESSION TRACKER — 6-10 Stakeholder Interviews
Session | Date | Participant(s) | Key Takeaways | Action Items | Status
Session 1
Session 2
Session 3
Session 4
Session 5
Session 6
Session 7
Session 8
Session 9
Session 10

## 2. Demand Sources
2. Demand Sources Mapping
Identify and map all demand entry points, channels, and current intake flows across Digital Products.
| Participants: | Core Team, BRS Liaison, demand sources representatives | Hacer el primer ejercicio y después mandar a validar con los intervinientes
| Duration: | 90-120 minutes
No. | Category | Question | Response / Findings | Ana Comments
1 | Demand Channels | List every channel through which work requests currently enter Digital Products. |  | Tener mapeado ya la slide Demand pero refinada con lo que sabemos y que sea complementarlo, conectarlo con reuniones existentes del governance
2 | Demand Channels | For each channel: who submits, how often, what type of work? |  | Tener mapeado ya la slide Demand pero refinada con lo que sabemos y que sea complementarlo, conectarlo con reuniones existentes del governance
3 | Intake Process | Is there a formal intake form or template? If so, what fields does it capture?
4 | Intake Process | How are requests classified today? (Type, priority, size, urgency)
5 | Intake Process | What happens after a request is submitted? Who triages it?
6 | Intake Process | How often do 'urgent' requests bypass the normal process?
7 | Demand Quality | What percentage of requests have clear business value or acceptance criteria?
8 | Demand Sources | Are there demand sources that Digital Products doesn't control? (External mandates, regulatory) |  | N/A, si hay, regulatory pero no sabemos cuantos y de que tipo el objetivo es entenderlo mejor para mapear bien esa parte
9 | Tooling | What tools are used to log/track demand today?
10 | Intake Process | What would need to be true for requestors to trust and consistently use a single intake channel?
11 | Performance | What's the average time from request submission to someone acknowledging it?
12 | Demand Patterns | Are there seasonal or cyclical patterns in demand? (Quarter-end, regulatory deadlines, budget cycles) |  | Mapeo de fechas clave
13 | Demand Quality | How many requests are duplicates or overlap with existing work? |  | Sabemos que pasa, por qué pasa, cual es el root cause
14 | Governance | What happens to requests that are rejected or deprioritized? Are requestors notified?
15 | Demand Channels | Is there demand that comes directly to individual developers bypassing any formal channel?
16 | Dependencies | Are there handoffs or dependencies in the intake process that slow things down or cause requests to get lost?
17 | Alignment | How involved are the requesting areas (BRS, OPCOs) in defining and validating what they need?
18 | Automation | Are there manual tasks in the intake process that could be automated?
SESSION TRACKER — 1-2 Demand Mapping Sessions
Session | Date | Participant(s) | Key Takeaways | Action Items | Status
Session 1
Session 2

## 3. Portfolio Review
3. Portfolio Review
Full view of active initiatives, scope, prioritization
|  | Participants: | Core team
|  | Duration: | 90-120 minutes
Hacer una revision mas general en lo que les gustaría minimo y no tanto foco en as is durante la sesion porque sabemos que no hay muchas cosas, que es para ellos valor y que debería medirse, tener de base un primer draft que permita priorizar ya sus opiniones
No. | Category | Question | Response / Findings
1 | Portfolio Definition | What types of initiatives are included in the portfolio (e.g., run, grow, transform)?
2 | Portfolio Definition | Is there a clear definition of what qualifies as a portfolio initiative? | No hay nivel de portfolio, mas bien es enseñar lo que se tiene y definir lo que haría sentido para ellos
3 | Inventory | Do you have a centralized and up-to-date view of all active initiatives? | Sabemos que no pero es "reconfirmar" o lo que ellos consideran lo mas up to date
4 | Inventory | How often is the portfolio inventory reviewed and updated?
5 | Prioritization | What criteria are used to prioritize initiatives? | No hay nivel de portfolio, mas bien es enseñar lo que se tiene y definir lo que haría sentido para ellos
6 | Prioritization | How do you balance business value, cost, and risk in prioritization? | No hay nivel de portfolio, mas bien es enseñar lo que se tiene y definir lo que haría sentido para ellos
7 | Prioritization | Who is responsible for prioritization decisions?
8 | Governance | Is there a formal governance structure for portfolio management? | N/A no existe pero queremos entender que sería lo equivalente y esto tiene que ver con tener mapeado el gobierno que nos han dado
9 | Governance | How are decisions escalated or resolved when there are conflicts?
10 | Governance | What committees, forums, or decision-making bodies are in place? | N/A, enseñar lo que se tiene y complementar en lo que falta
11 | Governance | How effective is the current governance in balancing speed and control?
12 | Alignment | How do you ensure initiatives align with strategic objectives?
13 | Alignment | Are strategic priorities clearly translated into the portfolio?
14 | Funding | How are initiatives funded and budgeted?
15 | Funding | Is funding fixed or flexible based on performance and priorities?
16 | Dependencies | Are there handoffs or dependencies that slow delivery?
17 | Dependencies | How do dependencies impact prioritization and delivery timelines?
18 | Dependencies | How do dependencies impact prioritization and delivery timelines?
19 | Tracking | What metrics or KPIs do you track regularly?
20 | Tracking | What tools or dashboards are used for portfolio tracking?
21 | Tracking | How do you track progress across initiatives?
22 | Performance | How do you measure the success of initiatives?
23 | Performance | How are these metrics used in decision-making?
24 | Performance | Are benefits tracked after delivery (value realization)?
25 | Visibility | Who has visibility into the portfolio and at what level of detail? | Se me duplica con anteriores
26 | Quality and Risk | How do you measure quality in delivery?
27 | Quality and Risk | How are risks and issues managed at the portfolio level?
28 | Quality and Risk | Is there a standardized way to report and mitigate risks?
SESSION TRACKER — 1-2 Portfolio Review Sessions
Session | Date | Participant(s) | Key Takeaways | Action Items | Status
Session 1
Session 2

## 4. Tool Ecosystem Review
4. Tool Ecosystem Review
Assess tools and fragmentation across lifecycle
|  | Participants: | Core Team, champions
|  | Duration: | 90-120 minutes
Introducir que es lo minimo que debería tener traceability desde su punto de vista (en cuanto a proceso end to end) y gestion del día a día de la organización
No. | Category | Question | Response / Findings
1 | Tool Inventory | What tools are currently used across the product and delivery lifecycle? | Se levanta durante demand y portfolio / conectar proceso + tool en el discovery
2 | Tool Inventory | Which tools are used for intake, prioritization, development, testing, and reporting? | Se levanta durante demand y portfolio / conectar proceso + tool en el discovery
3 | Tool Inventory | What challenges do you face in the current demand process related to tools? | Se levanta durante demand y portfolio / conectar proceso + tool en el discovery
4 | Workflow visibility | How well do your tools support visibility of the end-to-end flow of work?
5 | Tool Effectiveness | Which tools are most effective in managing delivery?
6 | Tool Effectiveness | Which tools are least effective in managing delivery?
7 | Workflow Gaps | Are bottlenecks or delays visible in your tools? If so, where?
8 | Workflow Dependencies | Are handoffs or dependencies between teams supported or tracked in tools? | Explicar bien vendors / software factory vs ellos
9 | Tool Ownership | Who owns and governs each tool?
10 | Tool Standardization | Are tools used consistently across teams or does each team use different ones? | No hay tools oficiales
11 | Tool Adoption | How do you know if a tool or way of working is truly adopted?
12 | Tool Usage | Are there any tools that are underutilized or duplicated?
13 | Integration | Are the tools integrated or mostly siloed?
14 | Integration | What are the main integration gaps between tools?
15 | Integration | How does information flow between tools (manual vs automated)?
16 | Performance | Do tools support tracking of delivery performance and KPIs effectively?
17 | Performance | What metrics or KPIs are tracked through your tools?
18 | Data & Reporting | How are these metrics generated and used within your tools?
19 | Data & Reporting | Where do you see gaps in measurement or data quality across tools?
20 | Data & Reporting | What data quality issues do you face?
21 | Data & Reporting | Do you have a single source of truth for portfolio and delivery data? | No lo tienen eso es lo que estamos intentando conseguir
22 | Data & Reporting | How easy is it to generate reports and dashboards? | [REMOVED — Redundant per Ana]
23 | User Experience | How intuitive and user-friendly are the current tools? | Redundante la quitaria
24 | User Experience | What are the main frustrations users have with the tools?
25 | Process Fit | Do the tools support your processes, or do teams adapt processes to fit the tools?
26 | Automation | What manual activities could be automated using existing or new tools?
27 | Automation | Are there opportunities to reduce handoffs through better tooling?
28 | Governance | Is there a defined strategy or roadmap for tools? | Sabemos que no, lo que hay que preguntar es PPM Tool (la nueva) y son preguntas relacionadas con el uso que se espera, mandatory cosas de Iberdrola y como eso tiene que conectar con lo que definamos
29 | Governance | How are decisions made when introducing or retiring tools?
30 | Security & Compliance | Are there any constraints related to security, compliance, or IT policies? | Redundante la quitaria
31 | Scalability | Can the current toolset scale with future needs and growth? | No escala y esta segmentado, ya lo sabemos y por eso estamos aquí, redundante
32 | Risks | Where do tools introduce risks to delivery quality?
SESSION TRACKER — 1-2 Tool Ecosystem Review Sessions
Session | Date | Participant(s) | Key Takeaways | Action Items | Status
Session 1
Session 2

## 5. Capacity & Resource Model
5. Capacity & Resource Model
Team structure, allocation model, delivery constraints
|  | Participants: | Executive SponsorProduct Owners, PMO
|  | Duration: | 90-120 minutes
Lo mismo, hay que enfocarlo más a como les gustaría evolucionarlo también como parte del speech y venir con un analisis de la info que nos trasladen sobre Roles y Responsabilidades para retarlo o alinearlo
No. | Category | Question | Response / Findings | Ana Comments
1 | Team Structure | How are teams currently structured (by product, function, or project)?
2 | Team Structure | What roles are involved in delivering initiatives?
3 | Team Structure | Are teams stable or formed dynamically per initiative?
4 | Team Collaboration | How do different teams or departments collaborate?
5 | Team Alignment | Where do you see silos, misalignments, or strong collaboration?
6 | Decision Making | Is decision-making centralized or decentralized by OpCo?
7 | Resource Allocation | How are resources allocated across initiatives?
8 | Resource Allocation | Who decides how resources are assigned?
9 | Resource Workload Balance | Where do you see over-allocation or underutilization of people?
10 | Resource Allocation | How often is resource allocation reviewed or adjusted?
11 | Resource Allocation Flexibility | How easily can resources be shifted across priorities or initiatives?
12 | Resource Allocation | How easily can people be reassigned across teams or initiatives?
13 | Capacity Planning | How do you estimate capacity for teams or individuals?
14 | Capacity Planning | How do you balance demand vs. available capacity?
15 | Planning Horizon | Over what time horizon do you plan capacity (e.g., sprint, quarter, year)?
16 | Capacity Planning | Is there a formal capacity planning process in place?
17 | Capacity Flexibility | How do you handle urgent or unplanned work?
18 | Skills & Capabilities | Do you have visibility into team skills and capability gaps?
19 | Skills & Capabilities | Do you see any skill gaps that limit delivery capacity?
20 | Skills & Capabilities | How are skill gaps currently addressed (e.g., hiring, training, external support)?
21 | Constraints | What are the main constraints impacting delivery (e.g., skills, availability, dependencies)?
22 | Constraints | Where do you typically see over-allocation or underutilization? | [REMOVED — Duplicate of Q10 per Ana] | Duplicada con la 10
23 | Dependencies | How do resource dependencies across teams impact delivery?
24 | Performance | How do you measure team productivity or efficiency?
25 | Performance | Are there metrics that link capacity to delivery outcomes?
26 | Governance | Is there a defined model or framework for capacity and resource management? |  | No hay
27 | Governance | Are responsibilities documented and accessible to everyone?
SESSION TRACKER — 1-2 Capacity & Resource Model Review Sessions
Session | Date | Participant(s) | Key Takeaways | Action Items | Status
Session 1
Session 2

## 6. Reporting & Metrics Review
6. Reporting & Metrics Review
Current reporting practices, KPIs, visibility gaps
|  | Participants: | Product Owners, PMO
|  | Duration: | 60-90 minutes
Traer de base al discutir, los KPIS definidos e implementados anteriores para ver cuales reusamos
No. | Category | Question | Response / Findings | Ana Comments
1 | KPI Framework | What KPIs are defined to measure product and delivery performance?
2 | KPI Framework | Are KPIs standardized across teams or defined independently?
3 | KPI Framework | How well do current KPIs align with business objectives?
4 | KPI Framework | How are these metrics used in decision-making?
5 | Metrics Coverage | What aspects of delivery are currently measured (e.g., speed, quality, value)?
6 | Metrics Coverage | Are there important areas that are not being measured today?
7 | Reporting | What reports or dashboards are regularly produced?
8 | Reporting | Who are the main consumers of these reports?
9 | Reporting | How frequently are reports generated and reviewed?
10 | Data Quality | How reliable and accurate is the data used for reporting?
11 | Data Quality | Are there inconsistencies across teams or systems?
12 | Data Availability | How easy is it to access the data needed for reporting?
13 | Data Ownership | Who owns the data and ensures its quality?
14 | Decision-Making | How are metrics used in decision-making processes?
15 | Decision-Making | Can you share examples where metrics influenced decisions?
16 | Actionability | Are reports actionable or mainly descriptive?
17 | Visibility | Do stakeholders have the right level of visibility into performance?
18 | Alignment | Is there alignment between operational metrics and strategic KPIs?
19 | Outcome Measurement | How do you measure business outcomes or value delivered?
20 | Outcome Measurement | Are benefits tracked after delivery (value realization)?
21 | Gaps & Pain Points | What are the main challenges with current reporting?
22 | Gaps & Pain Points | What improvements would make reporting more useful?
SESSION TRACKER — 1 Current reporting practices, KPIs, visibility gaps Review Sessions
Session | Date | Participant(s) | Key Takeaways | Action Items | Status
Session 1
Session 2