## Introduction
Digital Products — Discovery Sessions Workbook
New Ways of Working
Purpose
This workbook is the operational guide for all 8 Initial Discovery Sessions in Weeks 1-2 of the Digital Product project. Each tab contains the key questions to answer, context from the proposal, and space to capture responses and findings. Use this as the single source of truth for all baseline research.
Sessions Overview
Session | Number of Sessions | Duration | Purpose
1. Stakeholder Interviews | 6-10 sessions | 45-60 min each | Strategic priorities & pain points
2. Demand Sources Mapping | 1-2 sessions | 90-120 min | Map all entry points & channels
3. Portfolio Review | 1-2 sessions | 90-120 min | Full inventory of initiatives
4. Tool Ecosystem Review | 1-2 sessions | 90-120 min | Assess tools & fragmentation
5. Capacity & Resource Model | 1 session | 60-90 min | Team structure & constraints
6. Reporting & Metrics Review | 1 session | 60-90 min | Current KPIs & visibility gaps
7. Baseline Validation Workshop | 1 session | 90-120 min | Validate findings & align

## 1. Stakeholder Interviews
1. Stakeholder Interviews
Understand strategic priorities, operational challenges, and current pain points from both leadership and operational perspectives.
| Participants: | Executive Sponsor, Product Owners, PMO — 6-10 individual interviews
| Duration: | 45-60 minutes each
No. | Question | Description / Context | Response / Findings
1 | What is your role and how do you interact with Digital Products? | Map stakeholder's touchpoints: do they submit demand, receive deliveries, govern?
2 | What are your top priorities for the next 6 months? | Understand what drives each stakeholder — align lifecycle to their actual needs.
3 | Describe how a typical request goes from idea to delivery today. | Map the actual E2E flow per stakeholder — reveals bottlenecks and workarounds.
4 | Where do you experience the most friction or delays? | Identify pain points: handoff gaps, approval bottlenecks, communication breakdowns.
5 | How do you currently prioritize work? What criteria do you use? | Understand if value-based prioritization exists or if it's first-come-first-served / loudest voice.
6 | What tools do you use for tracking work? (Jira, ServiceNow, Excel, email?) | Map the tool landscape per stakeholder — reveals fragmentation.
7 | How do you get visibility into what's being worked on? | Assess reporting gaps: can they see status, dependencies, blockers?
8 | If you could fix ONE thing about how Digital Products operates today, what would it be? | Forces a single priority rather than a wish list — reveals the most painful issue per stakeholder
9 | What would make you say this project was a success? | Personal success criteria — essential for managing expectations.
10 | How are decisions escalated when there's a conflict between teams or priorities? | Map the escalation path: who has final say? How long does resolution take? This informs the governance model.
11 | What information do you need but currently don't have access to? | Identifies data and visibility gaps that the new operating model and dashboards must address.
12 | How do you measure the value delivered by Digital Products to your area? | Checks if there's any ROI or value tracking — critical for the Value Criteria Framework deliverable.
13 | If you could fix ONE thing about how work gets done today, what would it be? | Forces prioritization of pain points — the single most impactful answer per stakeholder.
14 | Is there anything you think we should know that we haven't asked? | Catch-all: often surfaces the most important insight.
15 | How is alignment ensured between Digital Products, SAP, BRS, and other consuming areas? | Cross-area alignment is often the #1 governance gap. With multiple directors and OPCOs, understanding how alignment works (or doesn't) is critical for the operating model
16 | Is decision-making centralized or distributed across areas? Where do you see silos? | Decentralized decisions often cause competing priorities. With 3 directors + VP, understanding the decision topology is critical for governance design
17 | How open is the culture to experimentation and new ways of working? | Change readiness assessment. Teams that resist new ways of working need a different approach. Knowing this upfront shapes the pilot strategy and change management plan
18 | What do you think is the biggest risk if we don't change how Digital Products operates? | Creates urgency and buy-in. The answer reveals whether stakeholders see this as optional or existential
19 | Who in the organization would you consider a natural champion for this initiative? Why? | Identifies natural allies and influencers. Having the right champions is the difference between adoption and resistance. Feeds directly into Champion Selection Selection
SESSION TRACKER — 6-10 Stakeholder Interviews
Session | Date | Participant(s) | Key Takeaways | Action Items | Status
Session 1
Session 2
Session 3
Session 4
Session 5
Session 6
Session 7
Session 8
Session 9
Session 10

## 2. Demand Sources
2. Demand Sources Mapping
Identify and map all demand entry points, channels, and current intake flows across Digital Products.
| Participants: | Product Owners, PMO, BRS Liaison, demand sources representatives
| Duration: | 90-120 minutes
No. | Question | Description / Context | Response / Findings
1 | List every channel through which work requests currently enter Digital Products. | Email, Teams, ServiceNow tickets, Jira, verbal in meetings, escalations — capture ALL of them.
2 | For each channel: who submits, how often, what type of work? | Map volume and type per channel to understand which are highest traffic.
3 | Is there a formal intake form or template? If so, what fields does it capture? | Assess current structure: title, description, priority, business value, acceptance criteria?
4 | How are requests classified today? (Type, priority, size, urgency) | Check if any classification exists: Strategic/Operational/Regulatory, S/M/L sizing, etc.
5 | What happens after a request is submitted? Who triages it? | Map the triage process: who reviews, how quickly, what criteria for accept/reject/clarify.
6 | How often do 'urgent' requests bypass the normal process? | Measure the informal/escalation path — often the real bottleneck.
7 | What percentage of requests have clear business value or acceptance criteria? | Assess quality of demand entering the system. Low quality = rework downstream.
8 | Are there demand sources that Digital Products doesn't control? (External mandates, regulatory) | Identify demand that can't be gated — must be accommodated in any new intake model.
9 | What tools are used to log/track demand today? | ServiceNow, Jira, Excel, email — map the current tool per channel.
10 | What would need to be true for requestors to trust and consistently use a single intake channel? | Reframed from 'ideal process' to 'adoption conditions'. The real question isn't what's ideal — it's what drives compliance
11 | What's the average time from request submission to someone acknowledging it? | Measure intake response time — a key baseline metric for the new SLA model.
12 | Are there seasonal or cyclical patterns in demand? (Quarter-end, regulatory deadlines, budget cycles) | Capacity planning needs: if demand spikes predictably, the intake model must accommodate it.
13 | How many requests are duplicates or overlap with existing work? | Quantify waste from lack of visibility — a strong argument for centralized intake.
14 | What happens to requests that are rejected or deprioritized? Are requestors notified? | Assess feedback loop to requestors — key for trust in any new intake process.
15 | Is there demand that comes directly to individual developers bypassing any formal channel? | Shadow demand: work that's invisible to leadership. Often the largest source of capacity drain.
16 | Are there handoffs or dependencies in the intake process that slow things down or cause requests to get lost? | Handoff gaps between intake and execution are a primary source of lost requests. Map every handoff point to identify where work gets stuck or dropped
17 | How involved are the requesting areas (BRS, OPCOs) in defining and validating what they need? | When requesting areas are excluded from validation, rework increases. Check if Digital Products involves requestors in defining and validating requirements
18 | Are there manual tasks in the intake process that could be automated? | Quick wins: if triage is manual email forwarding, a Jira intake form is an immediate improvement
SESSION TRACKER — 1-2 Demand Mapping Sessions
Session | Date | Participant(s) | Key Takeaways | Action Items | Status
Session 1
Session 2

## 3. Portfolio Review
3. Portfolio Review Session
Build a comprehensive view of active initiatives, scope, and prioritization across Digital Products.
| Participants: | Product Owners, PMO
| Duration: | 1-2 sessions — 90-120 minutes
No. | Question | Description / Context | Response / Findings
1 | How many active projects/initiatives are currently in flight? | Get the total count across all areas: SAP, Digital Apps, BRS, others.
2 | For each initiative: name, sponsor, start/end date, status, team size. | Build the portfolio inventory. This becomes the Portfolio Landscape deliverable.
3 | How are projects currently classified? (Type, size, strategic alignment) | Check if typology exists: Enhancement, New Build, Regulatory, Maintenance, etc.
4 | What is the current prioritization method? Who decides what gets done first? | Understand governance: is it VP-driven, committee-driven, or first-come-first-served?
5 | What are the cross-project dependencies? | Map dependencies that cause delays: shared resources, sequential deliverables, external teams.
6 | Which projects are at risk and why? | Identify the current portfolio health: blocked, delayed, under-resourced.
7 | How is project progress reported today? To whom? | Assess visibility: dashboards, status emails, weekly meetings?
8 | What SAP-specific initiatives are active and what's their relationship to other Digital Products work? | Map SAP projects specifically — these are the pilot focus area.
9 | Are there projects that should be stopped or deprioritized? | Identify waste: zombie projects consuming resources without clear value.
10 | What data sources exist for building a portfolio view? (Jira, PPMNow, spreadsheets) | Identify where to pull data for the Portfolio Landscape deliverable.
11 | What's the typical duration of a project from start to close? Any that have been running for over a year? | Identify long-running projects that may be zombie initiatives consuming resources without clear end.
12 | How are project budgets tracked and reported? Is there a link between effort and cost? | Financial visibility: essential for the PPMNow concept and investment model.
13 | Are there initiatives that span multiple areas (SAP + Digital Apps + BRS)? How are they coordinated? | Cross-cutting projects reveal coordination gaps that the lifecycle model must solve.
14 | What's the approval process for starting a new project? Who signs off? | Map the current governance gates — informs the Phase Gate design in the new lifecycle.
15 | Is there a formal project closure process? How are lessons learned captured? | Closing the loop: if projects never formally close, portfolio view is always inflated.
16 | How well do you understand the end-to-end flow of work from idea to delivery in your area? | Tests visibility at the portfolio level. If managers can't describe the full flow of work, it reveals a fundamental governance and transparency gap
17 | Are there standardized practices across project teams? Which ones work well, which don't? | Consistency check: if every project runs differently, the lifecycle design must account for variance. Lack of standards causes unpredictable deliveryelivery
18 | What's the total annual investment across the active portfolio? Is ROI tracked? | Financial perspective that pure process questions miss. Without knowing spend, you can't measure improvement. Senior consultants always ask this
SESSION TRACKER — 1-2 Portfolio Review Sessions
Session | Date | Participant(s) | Key Takeaways | Action Items | Status
Session 1
Session 2

## 4. Tool Ecosystem
4. Tool Ecosystem Review
Assess current tools and identify fragmentation across the product lifecycle.
| Participants: | Product Owners, PMO, Technical Leads
| Duration: | 1-2 sessions — 90-120 minutes
No. | Question | Description / Context | Response / Findings
1 | List every tool currently used across Digital Products (Jira, ServiceNow, Excel, Teams, PPMNow, etc.) | Complete inventory: tool name, purpose, who uses it, how many licenses.
2 | For each lifecycle phase (Intake → Prioritization → Execution → Reporting): which tools are used? | Map tools to lifecycle phases to visualize coverage and gaps.
3 | How is Jira currently configured? Projects, boards, workflows, issue types. | Understand the current Jira state — foundation for the Jira Config v1.0 deliverable.
4 | Is PPMNow in use? If so, what for? If not, what's the plan? | PPMNow is part of the target ecosystem — assess current state and readiness.
5 | Where does data get 'stuck' or require manual transfer between tools? | Identify integration gaps: manual CSV exports, copy-paste between systems, etc.
6 | What reporting exists today? What's automated vs. manual? | Assess the dashboard maturity: Jira dashboards, Excel reports, PowerBI, manual decks.
7 | Who has admin access to each tool? Is there a configuration owner? | Understand governance: who can change workflows, create projects, modify fields.
8 | What are the biggest tool-related frustrations from the team? | User experience insights: slow, confusing, duplicate entry, lack of training.
9 | Are there any planned tool changes or migrations in the next 6 months? | Avoid building on a platform that's about to change.
10 | Which tools and practices are most effective vs. least effective in managing delivery today? | Forces a concrete ranking instead of wishful thinking. Reveals what to keep vs. what to replace
11 | How many Jira projects exist today? Are there any unused or abandoned ones? | Jira hygiene: abandoned projects create noise. Cleanup is part of Jira Config v1.0.
12 | Is there a standard Jira workflow that all teams follow, or does each team have its own? | Fragmentation indicator: if every team has custom workflows, standardization effort is higher.
13 | How do teams track dependencies between projects in different tools? | Integration gap: if dependencies are tracked in email/spreadsheets, the tool ecosystem has a critical hole.
14 | What security or compliance requirements affect tool selection? (Data residency, access controls) | Constraints that may limit tool choices or configurations — must know before designing the target state.
15 | Is there a ServiceNow-to-Jira integration today? If not, how do tickets flow between them? | The proposal targets 'Intake → Jira → PPMNow'. Understanding the current ServiceNow↔Jira gap is critical.
16 | Are user interfaces and workflows standardized across teams using the same tools? | Different teams often use Jira completely differently — same tool, zero consistency. Understanding this directly impacts the Jira Config v1.0 design
17 | Are there manual tasks (copy-paste, email forwarding, spreadsheet updates) that could be eliminated with better tool integration? | Quantify automation opportunity: every manual step is a delay and error source
SESSION TRACKER — 1-2 Tool Ecosystem Sessions
Session | Date | Participant(s) | Key Takeaways | Action Items | Status
Session 1
Session 2

## 5. Capacity & Resources
5. Capacity & Resource Model Review
Understand team structure, allocation model, and delivery constraints.
| Participants: | Executive Sponsor, Product Owners, PMO
| Duration: | 1 session — 60-90 minutes
No. | Question | Description / Context | Response / Findings
1 | What is the current org structure of Digital Products? (teams, reporting lines, headcount) | Map the organizational structure: who reports to whom, team sizes, locations.
2 | How are resources currently allocated across projects? | Dedicated vs. shared resources. % allocation model or full-time assignment?
3 | What is the current team capacity per sprint/month/quarter? | Quantify: how many story points / hours / features can the team deliver?
4 | Are there shared resources across Digital Products, SAP, and other areas? | Identify resource contention: people stretched across multiple teams.
5 | What roles exist today? (PM, PO, Dev, QA, BA, Scrum Master, etc.) | Map actual roles vs. what the RACI matrix will need.
6 | What are the main delivery constraints? (skills gaps, availability, dependencies) | Identify what limits throughput: waiting for approvals, specialized skills, vendor dependencies.
7 | How is capacity currently tracked? Any tools or processes? | Assessment: is there resource planning today or is it ad-hoc?
8 | What happens when demand exceeds capacity? | Understand the overflow mechanism: queue, escalation, overtime, scope cut, delay?
9 | Is there a contractor/vendor capacity that supplements the core team? | Map extended team: NTT DATA, other vendors, contractors, offshore.
10 | What would need to change in the resource model to support the new lifecycle? | Forward-looking: identify resource model changes needed (even if out of scope for Wave 1).
11 | What's the current ratio of BAU/maintenance work vs. new development? | Capacity split: if 80% is BAU, there's little room for new lifecycle processes without addressing this.
12 | How are team members onboarded to new projects? Is there a standard process? | Onboarding speed affects delivery — if it takes weeks to ramp up, the pilot timeline is at risk.
13 | Are there skills that are concentrated in one person? (Single points of failure) | Key-person risk: if one person leaves, what breaks? Informs the RACI and succession planning.
14 | How does the team handle context-switching between multiple projects? | Multitasking tax: if people are on 3+ projects, effective capacity is much lower than theoretical.
15 | What's the team's experience with Kanban, Scrum, or other agile practices? | Agile maturity baseline: determines how much training is needed for the new WoW Playbook.
16 | How clear are responsibilities and decision rights across roles today? Do you experience overlaps or gaps? | Direct input for the RACI matrix deliverable. Unclear ownership causes both duplication of effort and tasks that fall through the cracks
17 | Are there tasks you're currently performing that you believe would be more appropriate for another role or team? | Reveals misalignment between actual work and role definition. Often surfaces the most actionable RACI fixes
18 | How is knowledge shared and retained when team members leave or change roles? | Knowledge management gap: if critical knowledge is in people's heads, every departure is a crisis

## 6. Reporting & Metrics
6. Reporting & Metrics Review
Understand current reporting practices, KPIs, and visibility gaps.
| Participants: | Product Owners, PMO
| Duration: | 1 session — 60-90 minutes
No. | Question | Description / Context | Response / Findings
1 | What reports are currently produced? By whom? How often? | Inventory all reporting: weekly status emails, monthly decks, Jira dashboards, etc.
2 | Who are the consumers of these reports? What decisions do they inform? | Map report → audience → decision to understand what's actually useful.
3 | What KPIs or metrics are currently tracked? | List current metrics: on-time delivery, throughput, cycle time, customer satisfaction, etc.
4 | How is project health assessed today? What signals a project is 'at risk'? | Understand the current health model: red/amber/green? Data-driven or gut feel?
5 | What data sources feed into current reporting? | Map data flow: Jira, ServiceNow, Excel, PPMNow, manual entry.
6 | What visibility gaps do leadership complain about most? | The VP's perspective: what can't they see that they need to see?
7 | How long does it take to produce a status report today? | Quantify manual effort: if it takes hours, automation is a key win.
8 | What would the ideal dashboard show? (real-time, drill-down, portfolio view) | Design the target: what metrics, what level of detail, what refresh rate.
9 | Are there any compliance or regulatory reporting requirements? | Identify non-negotiable reports that must be maintained.
10 | What metrics would indicate that the new operating model is working? | Define success metrics for the project itself — feeds into the KPI Framework deliverable.
11 | Who currently owns the reporting process? Is it centralized or distributed? | Ownership clarity: if nobody owns it, reports are inconsistent. If one person owns it, it's a bottleneck.
12 | What decisions have been made (or not made) due to lack of data or visibility? | Impact of reporting gaps: concrete examples make the case for automated dashboards.
13 | How do you track project costs vs. budget? Is this automated or manual? | Financial reporting maturity: essential for the PPMNow integration concept.
14 | Are there existing SLAs or service commitments that need to be measured? | SLA tracking informs what KPIs must exist from day one in the new framework.
15 | What's the biggest gap between what leadership wants to see and what's currently available? | The VP's wish list: directly informs the dashboard design in the KPI Framework deliverable.
16 | How do you measure quality in delivery? Are there quality gates or review checkpoints? | Quality metrics are often missing from KPI frameworks that only track speed. Definition of Done, defect rates, rework rates
17 | Are SLAs clear and consistently met? How do you know when one is breached? | SLA discipline: if SLAs exist but aren't monitored, the reporting framework must include SLA tracking from day one
18 | How are metrics used in actual decision-making? Can you give a recent example? | Tests if metrics drive action or just fill slides. If metrics don't change decisions, they're vanity metrics

## 7. Baseline Validation
7. Baseline Validation Workshop
Validate findings from all previous sessions, confirm key gaps, and align on the current state baseline.
| Participants: | Executive Sponsor, Product Owners, PMO, Management, BRS
| Duration: | 1 session — 90-120 minutes
No. | Question | Description / Context | Response / Findings
1 | Does the Current State summary accurately represent how Digital Products operates? | Present the synthesized findings. Get explicit agreement or corrections.
2 | Are the identified gaps and pain points correctly prioritized? | Validate that the biggest problems are what the team agrees are biggest.
3 | Is the Demand Map complete? Are there missing entry points or channels? | Final check on demand sources — any gaps mean the intake design will be incomplete.
4 | Does the Portfolio Landscape capture all active initiatives? | Validate completeness: missing projects = blind spots in the lifecycle design.
5 | Are there any findings that surprised you? | Surfaces unknown unknowns — often the most valuable insights.
6 | What should be the top priority for the Lifecycle Design (Step 2)? | Focus the next step: what's the most impactful area to define first?
7 | Are there any organizational sensitivities we should be aware of? | Political landscape: teams that resist change, competing agendas, leadership dynamics.
8 | Is there anything that should be added to or removed from the project scope? | Scope check: based on findings, does the scope still make sense?
9 | Do all stakeholders agree on the baseline? Any dissenting views? | Ensure alignment: disagreements now become blockers later.
10 | What are the key risks for Steps 2-5 based on what we've learned? | Risk register: resource availability, tool readiness, stakeholder commitment, etc.
11 | Based on the findings, what are the quick wins we can implement immediately? | Identify low-hanging fruit: changes that deliver value before the full lifecycle is designed.
12 | Which areas showed the most divergence in stakeholder perspectives? | Disagreements between stakeholders = areas that need explicit alignment before designing solutions.
13 | Are the recommended reuse items from other projects (P&S, CoE, DTO, Infra) acceptable? | Validate the Prior Art Review recommendations: any political or practical objections to reusing materials?
14 | What's the team's readiness for the BRS pilot in Weeks 7-13? | Pilot readiness check: do the pilot team members have availability? Are dependencies cleared?
15 | What communication should go out to the broader organization about this initiative? | Change management: who needs to know, what message, through what channel. Prevents surprises.
16 | What do you think is the biggest strength of the current organization that we should preserve? | Not everything needs to change. Identifying strengths prevents over-engineering and builds goodwill
17 | How will you know if a new process or tool is truly adopted vs. just nominally in place? | Adoption criteria: tools are often 'deployed' but not truly 'adopted'. Define what real adoption looks like before the pilot starts
18 | What resources and time commitment is each area willing to make for the BRS pilot? | Commitment check: oral agreement now becomes written commitment. Without explicit time allocation, the pilot will starve